## Sheet1
Date | Name | Progress | Any problems
2020-04-28 | Jacqueline | got GUI on eclipse | it was diffficult to get it work and I had to watch a bunch of youtube videos to figure out how it works
2020-05-02 | Meghana | figured out how get a GUI on eclipse | the GUI is not that easy to work, so I may face some dificulties connecting the two part
2020-05-03 | Both | got the GitHub to work on both ends | commit and push wasn't working, but we downloaded the desktop version and started commiting from there so it worked
2020-05-06 | Meghana | played around with source and design to get an idea of how to code for the game | none
2020-05-13 | Meghana | made the GameBoard class containing a 10 by 10 grid with buttons | not sure how to connect to the algorithm, but I can figure that out when the algorithm is done
2020-05-18 | Jacqueline | started to work on person vs person class | not sure how to elegantly output code and which data structures to use
2020-05-20 | Jacqueline | finished person vs person class | none
2020-05-21 | Jacqueline | started person vs computer class | did not know how to make the computer's map random; problems with making sure ships overlap; problems with how to optimize computer's guesses
2020-05-22 | Meghana | made a PersonVsComputerGUI class *later deleted* | unable to connect the GUI with the rest of the program
2020-05-23 | Jacqueline | finished person vs computer class | none
2020-05-24 | Meghana | started BattleShipGame class and made the start page | did not know how to make the action performed for the buttons start a new game
2020-05-25 | Meghana | tried to connect the GameBoard to the algorithm | unable to connect the GUI with the rest of the program